## Sheet1
Please note this checklist is in draft format, areas in blue indicate feedback required
FUNdamentalz Coach Course Set Up Check List | Required Min. time in advance | NSO | PSO | LF Resp
S=Support
C =Check
L= Lead
PRE COURSE:
Verify Learning Facilitator is active with Freestyle Canada | 9 weeks | L | S | S
Confirm appropriate terrain will be available (terrain guidelines in FC Resource Centre) | 9 weeks |  | L
Hire Learning Facilitor using FC template contract* | 8 weeks |  | L | S
Set up course on Goalline (or preferred registration method) | 6 weeks |  | L | C
Publish course details /Advise FC Coach Manager | 6 weeks | C | L | S
Request a Sanction and Certificate of Insurance from FC | 3 weeks |  | L | C
Send final registration list with email address's to LF | 3 weeks |  | L | C
Send link to FUNdamentalz pre-course website to candidates | 3 weeks | S | L | C
Email communication with registered candidates - meeting time/location/tickets/equip/etc | 3 weeks |  | C | L
Order Pocket Guides if needed | 3 weeks | S | L | C
Check pre course material completed from Candidates | 1 week |  | L | S/C
Follow up with Candidates if pre course material not completed | 1 week |  | L | S/C
Enter course/participants into The Locker | 2 days- week | S | C | L
Check internet access is available LF to during course (or they have web materials as needed) | 2 days- week |  | L | C
Check terrain is prepared pre course (LF should be confident with terrain and location) | 2 days- week |  | S | L
*Note in agreement who is resp for all above - P/TSO or LF?
MATERIALS:
FUNZ COACH POCKET GUIDES - PSO order hard copies from FC 2017/18 (3 weeks for shipping) Value $15 each plus shipping | 3 weeks | S | L | C
Laptop Computer | 1 week |  | C | L
FUNz LF Guide (download from FC Resource Centre) | 1 week | S | C | L
Small Rewards (approx 10)
POST COURSE:
Evaluations (excel format, FC Resource Centre- send to Candidate/PSO/NSO) | on-course or within 2 days |  | C | L
Entry into Locker | within 2 days |  | C | L
Follow-up on feedback on course to NSO/PSO | within 2 days |  | S | L
version Nov 3 2017